## Dashboard
RPS PERMIT TRACKER — DASHBOARD
Rappahannock Petroleum, LLC ¦ one row per permit
Refreshed: 08/12/2026
STATUS COUNTS |  | THE BIG ONE
Not Started | 9 | Unknown means Hash has not pulled the electrical yet, so we still do not know whether a building or mechanical permit is coming. Once the electrical is in hand, nothing else is needed and that row flips to None - confirmed at pull. Every Unknown inside 28 days of a work date is the thing that kills a schedule. Chase those first.
Submitted to Hash | 0
Hash Submitted Confirmed | 0
In Progress | 8
Permit In-Hand | 6 | WHAT EACH PERMIT IS WAITING ON
Inspection Scheduled | 0 | Permit ID | Jurisdiction | Pulled By | Status | Work Date | Waiting On
Complete | 0 | 32976-ELEC | Prince William County, VA | Hash | In Progress | 2026-08-13 | Confirm the USG permit was ever pulled. Work is 8/13.
On Hold | 1 | 34688-ELEC | Ranson / Jefferson Co, WV | Hash | Not Started | 2026-08-20 | Hash VA license does not cover WV. Confirm before filing.
Rejected | 1 | 34022-ELEC | Warren County, VA | Hash | In Progress | 2026-08-26 | Submit to inspections@warrencountyva.gov.
|  | 34022-BLDG | Warren County, VA | RPS | Not Started | 2026-08-26 | RPS has not started the building permit.
TOTAL PERMITS TRACKED | 25 | 23689-ELEC | Baltimore City, MD | Hash | On Hold | 2026-09-01 | Proof of ownership. Deed submitted 3/13.
|  | 32258-ELEC | Warren County, VA | Hash | In Progress | 2026-09-10 | Owner signature for zoning.
ATTENTION |  | 32258-BLDG | Warren County, VA | RPS | Not Started | 2026-09-10 | RPS has not started the building permit.
Past due and not in hand | 5 | 17206-ELEC | Culpeper, VA | Hash | Not Started | 2026-09-22 | Confirm town vs county, then file.
Due in the next 14 days | 3 | 30479-ELEC | Fairfax County, VA | Hash | Not Started | 2026-09-24 | Confirm jurisdiction, then file.
Electrical not yet pulled - extras still Unknown | 12 | 33962-ELEC | Calvert County, MD | Hash | Rejected |  | Find out why it was rejected before resubmitting.
FIX ME: electrical in hand but still says Unknown | 0 | 33599-ELEC | Fairfax County, VA | Hash | Not Started |  | Work date from 7-Eleven.
Electrical permits (Hash pulls) | 22 | 33714-ELEC | City of Manassas Park, VA | Hash | Not Started |  | File with the city, not the county.
Building + Mechanical permits (RPS pulls) | 3 | 36798-ELEC | Loudoun County, VA | Hash | Not Started |  | Confirm Loudoun vs Fairfax.
No work date set yet | 10 | 33701-ELEC | Stafford County, VA | Hash | In Progress |  | Work date, then submit.
|  | 18245-ELEC | Shenandoah County, VA | Hash | In Progress |  | Work date, then submit.
OPEN ITEMS ON THE 7/28 DRAWING SET (11 SITES) |  | 45967-ELEC | City of Harrisonburg, VA | Hash | In Progress |  | Drawing final. Confirm Hash holds a City of Harrisonburg business license, then file.
Page 3 General Note 1 on all eleven names Gilbarco Encore 300 as the existing unit. That belongs to 34022 only. Replace it with the generic swap note on the other ten. |  | 24603-ELEC | Henrico County, VA | Hash | In Progress |  | E.C. Livingston signature, then Erin Zust pulls it.
All eleven still carry 34022 data under the artwork. Only 24603 got the pixel rebuild. Rebuild before any portal upload. |  | 24603-MECH | Henrico County, VA | RPS | Not Started |  | RPS has not started the mechanical permit.
The 7/28 session said "four sites have diesel" but listed only three: 32258, 17206, 36798. If there is a fourth, its drawing says 3+0 and is wrong. |  | HM-6-ELEC | City of Winchester, VA | Hash | In Progress |  | Value of construction and date, then upload to OpenGov.
Files: Mac Studio > Permitting Apps > [site] Permit Docs, plus a combined Hash Dispenser Replacement Permit docs folder.

## Permits
Permit ID | Site # | Site Name | Address | City | State | Jurisdiction | Project Type | Request Type | Permit Type | Pulled By | Requirement | Status | Other Permits Required | Scheduled Work Date | Permit Due Date | Days Until Due | Submitted to Hash | Hash Confirmed | Submitted to Jurisdiction | Permit # | Fee | Date Issued | Inspection Date | Date Complete | Notes
33955-ELEC | 33955 | 7-Eleven #33955 | 7489 Limestone Drive | Gainesville | VA | Prince William County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Permit In-Hand | None - confirmed at pull | 2026-07-14 | 2026-06-16 | Have it | [8 empty] | Permit in hand, VA electricians confirmed. Work date 7/14 has passed - confirm the work and inspection are done and move this to Complete.
29104-ELEC | 29104 | 7-Eleven #29104 | 11007 Nokesville Road | Manassas | VA | Prince William County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Permit In-Hand | None - confirmed at pull | 2026-07-16 | 2026-06-18 | Have it | [8 empty] | Permit in hand, VA electricians confirmed. Work date 7/16 has passed - confirm the work and inspection are done and move this to Complete.
26941-ELEC | 26941 | 7-Eleven #26941 | 15621 Jefferson Davis Highway | Woodbridge | VA | Prince William County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Permit In-Hand | None - confirmed at pull | 2026-07-22 | 2026-06-24 | Have it | [8 empty] | Permit in hand, VA electricians confirmed. Work date 7/22 has passed - confirm the work and inspection are done and move this to Complete.
30484-ELEC | 30484 | 7-Eleven #30484 | 17105 Old Stage Road | Dumfries | VA | Prince William County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Permit In-Hand | None - confirmed at pull | 2026-07-28 | 2026-06-30 | Have it | [8 empty] | Permit in hand. Waiting for electricians to confirm. Work date 7/28 has passed - confirm status.
32223-ELEC | 32223 | 7-Eleven #32223 | 6865 Wellington Rd | Manassas | VA | Prince William County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Permit In-Hand | None - confirmed at pull | 2026-07-30 | 2026-07-02 | Have it | [8 empty] | Permit in hand. Waiting for electricians to confirm. Work date 7/30 has passed - confirm status.
28960-ELEC | 28960 | 7-Eleven #28960 | 11108 Angleberger Rd | Thurmont | MD | Frederick County, MD | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Permit In-Hand | None - confirmed at pull | 2026-09-15 | 2026-08-18 | Have it | [8 empty] | Permit in hand. Schedule with the canopy replacement per Paul Encinas. Work date 9/15.
32976-ELEC | 32976 | 7-Eleven #32976 | 10438 Dumfries Road | Manassas | VA | Prince William County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | In Progress | Unknown - pending Hash | 2026-08-13 | 2026-07-16 | -27 | [8 empty] | MUL conversion, not a standard swap. Drawing built 7/28. USG permit status never confirmed - raised 7/28, still open. Work is 8/13 and the due date passed 27 days ago.
34688-ELEC | 34688 | 7-Eleven #34688 | 809 N Mildred Street | Ranson | WV | Ranson / Jefferson County, WV | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Not Started | Unknown - pending Hash | 2026-08-20 | 2026-07-23 | -20 | [8 empty] | WV site. Hash Class A 2705048270 is a VIRGINIA license and does not cover West Virginia. Confirm Hash can legally pull here and whether Ranson or Jefferson County issues it. Work is 8/20.
34022-ELEC | 34022 | 7-Eleven #34022 | 251 Crooked Run Plaza | Front Royal | VA | Warren County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | In Progress | Building - CONFIRMED | 2026-08-26 | 2026-07-29 | -14 | [8 empty] | Application filled and flattened. MDIA form required. Email to inspections@warrencountyva.gov.
34022-BLDG | 34022 | 7-Eleven #34022 | 251 Crooked Run Plaza | Front Royal | VA | Warren County, VA | Dispenser Replacement | Non-PE Stamped | Building | RPS | Required | Not Started |  | 2026-08-26 | 2026-07-29 | -14 | [8 empty] | Warren County requires a building permit on this one. RPS pulls it. Not started.
23689-ELEC | 23689 | 7-Eleven #23689 | 2701 W Franklin St | Baltimore | MD | Baltimore City, MD | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | On Hold | Unknown - pending Hash | 2026-09-01 | 2026-08-04 | -8 | [8 empty] | No drawing built. Proof of ownership outstanding - deed submitted 3/13 and still not cleared. Baltimore City, not Baltimore County.
32258-ELEC | 32258 | 7-Eleven #32258 | 711 S. Royal Ave | Front Royal | VA | Warren County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | In Progress | Building - CONFIRMED | 2026-09-10 | 2026-08-13 | 1 | [8 empty] | Application filled and flattened. Prioritize per David Arnette 6/30/26. Waiting on owner signature for zoning. MDIA form required.
32258-BLDG | 32258 | 7-Eleven #32258 | 711 S. Royal Ave | Front Royal | VA | Warren County, VA | Dispenser Replacement | Non-PE Stamped | Building | RPS | Required | Not Started |  | 2026-09-10 | 2026-08-13 | 1 | [8 empty] | Warren County requires a building permit on this one. RPS pulls it. Not started.
17206-ELEC | 17206 | 7-Eleven #17206 | 520 James Madison Highway | Culpeper | VA | Culpeper County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Not Started | Unknown - pending Hash | 2026-09-22 | 2026-08-25 | 13 | [8 empty] | Drawing built 7/28, 3+1 diesel. Confirm Town of Culpeper vs Culpeper County before filing.
30479-ELEC | 30479 | 7-Eleven #30479 | 6221 Rolling Road | Springfield | VA | Fairfax County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Not Started | Unknown - pending Hash | 2026-09-24 | 2026-08-27 | 15 | [8 empty] | Drawing built 7/28, 3+0.
33962-ELEC | 33962 | 7-Eleven #33962 | 3675 Hallowing Point Road | Prince Frederick | MD | Calvert County, MD | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Rejected | None - building not required | [11 empty] | No building permit needed, already confirmed. Electrical was rejected and must be resubmitted - find out why before resending the same package. No drawing built.
33599-ELEC | 33599 | 7-Eleven #33599 | 14533 Lee Rd | Chantilly | VA | Fairfax County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Not Started | Unknown - pending Hash | [11 empty] | Drawing built 7/28, 3+0.
33714-ELEC | 33714 | 7-Eleven #33714 | 101 Kent Village Square | Manassas Park | VA | City of Manassas Park, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Not Started | Unknown - pending Hash | [11 empty] | Drawing built 7/28, 3+0. Independent city - files with Manassas Park, not Prince William County.
36798-ELEC | 36798 | 7-Eleven #36798 | 25140 Loudoun County Pkwy | Chantilly | VA | Loudoun County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | Not Started | Unknown - pending Hash | [11 empty] | Drawing built 7/28, 3+1 diesel. Confirm Loudoun vs Fairfax. Inform Paul Encinas upon completion.
33701-ELEC | 33701 | 7-Eleven #33701 | 2998 Jefferson Davis Highway | Stafford | VA | Stafford County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | In Progress | Unknown - pending Hash | [11 empty] | Application filled and flattened. Stafford form: Tenant = SAME AS OWNER, Applicant = SAME AS CONTRACTOR.
18245-ELEC | 18245 | 7-Eleven #18245 | 285 W. Old Cross Rd | New Market | VA | Shenandoah County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | In Progress | Unknown - pending Hash | [11 empty] | Application filled and flattened. One combined Shenandoah form covers all trades.
45967-ELEC | 45967 | Speedway #45967 | 1437 S Main St | Harrisonburg | VA | City of Harrisonburg, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | In Progress | Unknown - pending Hash | [11 empty] | Drawing FINAL 8/12 - this is the new master form for dispenser drawings. Speedway brand, but 7-Eleven owns Speedway, so the owner block is the standard 7-Eleven Dallas block. Replace (6), RUL/PUL/DSL so 3+1. Harrisonburg is an independent city, NOT Rockingham County. City wants the state Class A AND a City of Harrisonburg business license number. Electrical in before 3:00 PM is usually issued same day.
24603-ELEC | 24603 | 7-Eleven #24603 | 2111 Hilliard Rd | Henrico | VA | Henrico County, VA | Dispenser Replacement | Non-PE Stamped | Electrical | Hash Construction | Required | In Progress | Mechanical - CONFIRMED | [11 empty] | Drawing complete, Hash block, zero instances of the word new. Waiting on E.C. Livingston signature and date, then Erin Zust pulls it.
24603-MECH | 24603 | 7-Eleven #24603 | 2111 Hilliard Rd | Henrico | VA | Henrico County, VA | Dispenser Replacement | Non-PE Stamped | Mechanical | RPS | Required | Not Started | [12 empty] | Henrico requires a mechanical permit on this one. RPS pulls it. Not started.
HM-6-ELEC | HM-6 | Handy Mart #6 | 2605 Valley Ave | Winchester | VA | City of Winchester, VA | STP Circuit Repair | Non-PE Stamped | Electrical | Hash Construction | Required | In Progress | Unknown - pending Hash | [11 empty] | STP branch circuit repair, not a dispenser swap. Owner is H.N. Funkhouser & Co., PO Box 2038, Winchester VA 22604. Value of construction and date still blank. Upload to winchesterva.portal.opengov.com.
Formulas:
Permit Due Date = IF([Scheduled Work Date]="","",[Scheduled Work Date]-28)
Days Until Due = IF([Permit Due Date]="","",IF(OR([Status]="Permit In-Hand",[Status]="Inspection Scheduled",[Status]="Complete"),"Have it",[Permit Due Date]-TODAY()))

## Workflow & Status Key
HOW A PERMIT MOVES
Step 1 — Request type | Decide if the job needs PE stamped plans. Almost everything we do is Non-PE Stamped. When stamped plans are required, an engineering firm usually pulls the permit and we track it here anyway.
Step 2 — Electrical first | Every dispenser replacement starts with Hash pulling the electrical permit. Nothing else is assumed at this point.
Step 3 — Discovery | We find out what else the jurisdiction wants when Hash tries to pull. Some want a building permit too. Some want a mechanical. Some want neither. Until Hash reports back, the Other Permits Required column stays Unknown.
Step 3a — The shortcut | If the electrical permit is already in hand, nothing else is needed. Full stop. The jurisdiction would have said so at the counter. Any electrical sitting at Permit In-Hand or later gets Other Permits Required set to None - confirmed at pull, and no building or mechanical row is created.
Step 4 — Split it out | The moment a building or mechanical permit is confirmed, add its own row. One row per permit, never two permits on one line. RPS pulls building and mechanical. Hash pulls electrical.
Step 5 — Work the ladder | Each permit row moves through the status ladder below on its own. A site is not ready to work until every required permit says Permit In-Hand.
STATUS LADDER
Not Started | Nothing sent yet.
Submitted to Hash | We handed the package to Hash. Hash-pulled permits only. For an RPS-pulled building or mechanical, skip to Submitted to Jurisdiction.
Hash Submitted Confirmed | Hash confirmed they actually filed it with the jurisdiction. Do not mark this off an assumption - get the confirmation.
In Progress | The jurisdiction has it and is reviewing.
Permit In-Hand | Permit issued and in our possession. This is the only status that clears a site to work.
Inspection Scheduled | Work done or scheduled and the inspection is on the calendar.
Complete | Inspection passed and the permit is closed out.
On Hold | Blocked by something outside the jurisdiction, like a missing owner signature or proof of ownership.
Rejected | Kicked back. Record why in Notes before resubmitting.
WHO PULLS WHAT
Electrical | Hash Construction, Inc. Always. VA license 2705048270 Class A, exp 03/31/2027. Virginia only - it does not cover Maryland or West Virginia.
Building | RPS. License 2705096729 Class A, exp 01/31/2027.
Mechanical | RPS. Same license.
PE Stamped jobs | Usually the engineering firm pulls it. Track it here regardless so the site status is complete.

## Jurisdiction Contacts
Jurisdiction | State | Department | Contact Name | Direct Phone | Email | Portal / Submittal Method | Turnaround | Fee Notes | Cheat Sheet Notes
Warren County | VA | Building Inspections |  | (540) 636-9973 | inspections@warrencountyva.gov | Digital submission by email |  |  | MDIA form required with every electrical permit. BUILDING PERMIT ALSO REQUIRED on 32258 and 34022 - RPS pulls those.
Henrico County | VA | Building Construction & Inspections |  | (804) 501-4360 |  |  |  |  | Inspections (804) 629-9782. MECHANICAL PERMIT ALSO REQUIRED on 24603 - RPS pulls it.
City of Harrisonburg | VA | Community Development - Building Inspections, 409 S Main St 2nd Floor |  | (540) 432-7700 | permits@harrisonburgva.gov | LAMA Permit Portal, email, or in person | Electrical before 3 PM usually same day | Based on total value of electrical work. Check payable to City of Harrisonburg. | Independent city, NOT Rockingham County. Contractor must supply state Class A/B/C AND a City of Harrisonburg business license number. Portal needs a contractor registration code - call to get one.
City of Winchester | VA | Building / Zoning, Rouss City Hall | Tom Mayhew; Richie Fletcher | (540) 667-1815 |  | winchesterva.portal.opengov.com |  |  | City, not Frederick County. No downloadable form - upload our own written application. MDIA (540-667-8484) is inspections only.
Stafford County | VA | Public Works / Building Division |  | (540) 658-8650 |  |  |  |  | Tenant = SAME AS OWNER, Applicant = SAME AS CONTRACTOR.
Shenandoah County | VA | Community Development |  | (540) 459-6185 |  |  |  |  | One combined application form covers all trades.
Prince William County | VA | Development Services / Building Development | [6 empty] | 32976 is a MUL conversion. USG permit status unconfirmed.
Loudoun County | VA | Planning | Alex Wilkinson | (703) 771-5353 | Alex.Wilkinson@Loudoun.gov |  |  |  | Confirm whether 36798 falls in Loudoun or Fairfax.
Fairfax County | VA | Land Development Services | [6 empty] | NEEDS RESEARCH - covers 30479 and 33599.
City of Manassas Park | VA | Building Official | [6 empty] | NEEDS RESEARCH - independent city, files separately from Prince William.
Culpeper (town vs county) | VA | [7 empty] | NEEDS RESEARCH - confirm which office covers 520 James Madison Hwy.
Baltimore City | MD | Dept of Housing & Community Development | [6 empty] | NEEDS RESEARCH - proof of ownership outstanding for 23689.
Calvert County | MD | Inspections & Permits | [6 empty] | NEEDS RESEARCH - building confirmed not required. Electrical rejected, must resubmit.
Ranson / Jefferson County | WV | [7 empty] | NEEDS RESEARCH - confirm issuing office and whether Hash holds a WV license.
Rockingham County | VA | Development Center |  | (540) 437-2354 |  |  |  |  | Does NOT cover Harrisonburg addresses. Harrisonburg is an independent city.
MDIA (third-party inspections) | VA | 3078 Shawnee Dr Ste A, Winchester VA 22601 |  | (540) 667-8484 |  |  |  |  | Inspection agency only. Does not issue permits.

## Deliverables Log
Date | Site # | Deliverable | File Name | Where It Lives | Open Items
2026-07-28 | 32976 | Dispenser electrical drawing | 32976 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+0. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | 34688 | Dispenser electrical drawing | 34688 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+0. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | 34022 | Dispenser electrical drawing | 34022 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+0. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | 32258 | Dispenser electrical drawing | 32258 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+1 DSL. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | 17206 | Dispenser electrical drawing | 17206 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+1 DSL. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | 30479 | Dispenser electrical drawing | 30479 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+0. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | 33599 | Dispenser electrical drawing | 33599 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+0. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | 33714 | Dispenser electrical drawing | 33714 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+0. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | 36798 | Dispenser electrical drawing | 36798 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+1 DSL. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | 33701 | Dispenser electrical drawing | 33701 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+0. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | 18245 | Dispenser electrical drawing | 18245 dispenser electrical drawing.pdf | Mac Studio > Permitting Apps > [site] Permit Docs | 3+0. FIX: page 3 General Note 1 carries 34022 Encore 300 wording. Replace with the generic swap note. 34022 residue in artwork.
2026-07-28 | ALL | Drawing template rules | Dispenser electrical drawing template.md | Project knowledge
2026-08-07 | 24603 | Dispenser electrical drawing | 24603_Dispenser_Electrical_Drawing.pdf | Chat download | Hash block. Zero instances of the word new. Artwork rebuilt clean. Needs E.C. Livingston signature and date.
2026-08-07 | - | Contact directory | RPS_Contact_Directory.xlsx | Chat download | Re-upload to look up contacts. Raw vcf not stored.
2026-08-10 | HM-6 | Scope narrative + 1-page application | HandyMart6 scope + application PDFs | Chat download | Value of construction and date still blank.
2026-08-12 | 45967 | Dispenser replacement drawing - FINAL | 45967_Dispenser_Replacement_Drawing.pdf | Chat download | MASTER FORM for all future dispenser drawings. All 3 pages rebuilt clean vector. 3+1. Generic General Note 1 - no existing model named. Zip added to page 1. Zero residue: no B05, no Encore 300, no 34022, no 24603, no Starsky/Dodson, no signature line, no instance of the word new.
2026-08-12 | ALL | Permit tracker v2 | RPS_Permit_Tracker.xlsx | Upload to project knowledge | Source of truth. Upload the current copy at the start of every permitting chat.

## Standard Info
STANDARD PARTIES — USE ON EVERY APPLICATION
OWNER (every 7-Eleven permit)
Company | 7-Eleven, Inc.
Attn | David Arnette
Address | PO Box 711, Dallas, TX 75221-0711
Phone | (757) 506-9329
Email | david.arnette@7-11.com
Rule | Always the Dallas PO Box. Never the job site address.
Speedway sites | 7-Eleven purchased Speedway, so Speedway sites use this exact same owner block. Site 45967 included.
Other brands | Handy Mart #6 is H.N. Funkhouser & Co., PO Box 2038, Winchester VA 22604. That is the only job on the board with a different owner.
RPS — BUILDING AND MECHANICAL PERMITS
Company | Rappahannock Petroleum LLC
Attn | Starsky Dodson
Address | 225 Ritter Rd, Winchester, VA 22602
Phone | (540) 869-5033
Fax | (540) 869-5406
License # | 2705096729, Class A
License Exp | 01/31/2027
Federal ID (EIN) | 202347099
HASH — ELECTRICAL PERMITS
Company | Hash Construction, Inc.
Address | 9290 W and W Industrial Rd, La Plata, MD 20646
Phone | (301) 870-6195
Permit Technician | Erin Zust — erinzust@hashconstruction.com
Signing Officer | E.C. Livingston — eclivingston@hashconstruction.com, x123
License # | 2705048270, Class A
License Exp | 03/31/2027
Rule | RPS does not appear on permits where Hash is the contractor of record.
Watch | That license is Virginia. It does not cover Maryland or West Virginia.
DEFAULTS
Request Type | Non-PE Stamped unless the jurisdiction demands sealed plans.
Work Type | Renovation. Repair when it is a like-for-like fix.
Use Group | Mercantile (M). Never Business.
Occupancy | Convenience store with fuel sales.
Permit Due Date | Scheduled work date minus 28 days. Two weeks is the hard floor.
Job Site Format | 7-Eleven #[site number], [address], [city], ST zip
State Fields | Two-letter abbreviation always: VA, MD, TX.
File Naming | Filled permit filenames start with the site number.
Seal-off Language | "No work below the seal-off or shear valve" goes on dispenser replacement scopes ONLY. Never on STP, tank pad, trenching, or underground branch circuit scopes.
Used Dispenser Drawings | Zero instances of the word "new" anywhere in the document.
Master Drawing Form | 45967_Dispenser_Replacement_Drawing.pdf (08/12/2026) is the current master form. Build every new dispenser drawing off that file, not off an older site drawing.
Existing Model Wording | Never carry an existing-dispenser model from one site drawing to another. Advantage B05 belongs to 24603 only. Encore 300 belongs to 34022 only. When the existing model is not confirmed, page 3 General Note 1 reads: "Like for like dispenser swap. Existing dispensers will be replaced with Gilbarco Encore 700 dispensers."
Conduit Standard | 3x #12 THWN-2 in 3/4" conduit for a 1.5 HP STP (validated against stamped plans, project 17219).